## Agile Sprint 1
Backlog Task & ID | Story | Assigned to | Status | Original | Day 1 | Day 2 | Day3 | Day 4 | Day 5 | Sprint
User Story #1 Login | 1 |  |  | 6
Backend Development (Database & API) |  | Pankaj | Done |  | 0 |  | 0 | 0 | 0 | 1
Frontend Development |  | Pankaj | Done | 4 | 2 | 0 | 0.5 | 3.5 | 0.25 | 4.25
Testing |  | Pankaj | Done | 1 | 1 | 0 | 0 | 0 | 0.5 | 0.5
User Story #2 Register | 1 |  |  | 6
Backend Development (Database & API) |  | Pankaj | Done | 1.5 | 0 | 0 | 1 | 0.5 | 0 | 1.5
Frontend Development |  | Pankaj | Done | 4 | 2 | 0 | 0 | 3 | 0.25 | 3.25
Testing |  | Pankaj | Done | 0.5 | 1 | 0 | 0 | 0 | 1 | 1
User Story #3 About Us | 1 |  |  | 6
Backend Development (Database & API) |  | Pankaj | Done | 1 | 1 | 1 | 0 | 0 | 0 | 1
Frontend Development |  | Pankaj | Done | 4.5 | 1 | 0 | 0 | 3 | 1 | 4
Testing |  | Pankaj | Done | 0.5 | 1 | 0 | 0 | 0 | 1 | 1
User Story #4 Search Bar | 1 |  |  | 6
Frontend Development |  | Pankaj | Done | 1 | 1 | 0.5 | 0.25 | 1.25 | 0.25 | 2.25
|  | Total |  | 24 | 0 | 2.5 | 1.75 | 11.25 | 4.25 | 19.75
|  | Ideal Time |  | 24 | -4.8 | -2.3 | -3.05 | 6.45 | -0.55 | 19.75

## Agile Sprint 2
Backlog Task & ID | Story | Assigned to | Status | Original | Day 1 | Day 2 | Day3 | Day 4 | Day 5 | Sprint
User Story #5 Hot Deals | 2 |  |  | 12
Backend Development (Database & API) |  | Pankaj | Done | 5 | 1.5 | 0.5 | 0 | 0 | 1 | 1.5
Frontend Development |  | Pankaj | Done | 5 | 1.5 | 0 | 1 | 2 | 6 | 9
Testing |  | Pankaj | Done | 2 | 1 | 0 | 0 | 0 | 1 | 1
User Story #6 Features | 1 |  |  | 6
Backend Development (Database & API) |  | Pankaj | Done | 3 | 2 | 0.5 | 0 | 0.25 | 1 | 1.75
Frontend Development |  | Pankaj | Done | 2 | 2 | 0 | 2 | 0 | 0 | 2
Testing |  | Pankaj | Done | 1 | 1 | 0 | 0 | 0 | 1 | 1
User Story #7 Logo | 1 |  |  | 6
Backend Development (Database & API) |  | Pankaj | Done | 3 | 1 | 0 | 0.25 | 0 | 0 | 0.25
Frontend Development |  | Pankaj | Done | 2 | 1 | 0 | 0 | 0.5 | 0.5 | 1
Testing |  | Pankaj | Done | 1 | 1 | 0 | 0.25 | 0 | 0 | 0.25
User Story #8 About | 1 |  |  | 6
Backend Development (Database & API) |  | Pankaj | Done | 1 | 1 | 0 | 0.25 | 0 | 0 | 0.25
Frontend Development |  | Pankaj | Done | 4 | 1 | 0 | 0 | 0 | 0.75 | 0.75
Testing |  | Pankaj | Done | 1 | 1 | 0 | 0 | 0 | 0 | 0
User Story #9Features Products | 1 |  |  | 6
Backend Development (Database & API) |  | Pankaj | Done | 1.5 | 1 | 0 | 0 | 0 | 1.75 | 1.75
Frontend Development |  | Pankaj | Done | 3.5 | 1 | 0.25 | 1 | 1.25 | 0 | 2.5
Testing |  | Pankaj | Done | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | Total |  | 36 | 0 | 1.25 | 4.25 | 4 | 13 | 23
|  | Ideal Time |  | 36 | -7.2 | -5.95 | -2.95 | -3.2 | 5.8 | 23

## Agile Sprint 3
Backlog Task & ID | Story | Assigned to | Status | Original | Day 1 | Day 2 | Day3 | Day 4 | Day 5 | Sprint
User Story #10 Banner | 1 |  |  | 6
Backend Development (Database & API) |  | Pankaj | To Do | 1 | 1 | 0 | 0.5 | 0 | 0 | 0.5
Frontend Development |  | Pankaj | Doing | 4 | 1 | 0.5 | 0.25 | 0 | 0 | 1
Testing |  | Pankaj | To Do | 1 | 1 | 0 | 0 | 0 | 0 | 0
User Story #11 Newsletter | 1 |  |  | 6
Backend Development (Database & API) |  | Pankaj | To Do | 2.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 2.5
Frontend Development |  | Pankaj | Doing | 2.5 | 1 | 0.5 | 1 | 0 | 0 | 1.75
Testing |  | Pankajj | To Do | 1 | 1 | 0 | 0 | 0 | 0 | 0
User Story #12 Contact | 2 |  |  | 12
Backend Development (Database & API) |  | Samishan | To Do | 5.5 | 1 | 0.5 | 0.5 | 0 | 0 | 1
Frontend Development |  | Manoram | To Do | 5.5 | 1 | 1.5 | 0.5 | 0 | 0 | 2
Testing |  | Manoram | To Do | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | Total |  | 24 | 0.5 | 4 | 3.25 | 0.5 | 0.5 | 8.75
|  | Ideal Time |  | 24 | -4.3 | -0.8 | -1.55 | -4.3 | -4.3 | 8.75

## Agile Sprint 4
Backlog Task & ID | Story | Assigned to | Status | Original | Day 1 | Day 2 | Day3 | Day 4 | Day 5 | Sprint
User Story #10 Search Properties | 0.5 |  |  | 3
Backend Development (Database & API) |  | Samishan | Done | 1 | 0 | 0 | 0.75 | 0.5 | 0 | 1.25
Frontend Development |  | Gokarna | Done | 1 | 0 | 0 | 0.5 | 0.5 | 0 | 1
Testing |  | Samishan | Done | 1 | 0 | 0 | 0.5 | 0 | 0 | 0.5
User Story #11 Filter Out Properties | 1 |  |  | 6
Backend Development (Database & API) |  | Prathana | Done | 2.5 | 0 | 0.5 | 0.5 | 1 | 0.5 | 2.5
Frontend Development |  | Namrata | Done | 2.5 | 0 | 0.5 | 0.5 | 1 | 0.5 | 2.5
Testing |  | Prathana | Done | 1 | 0 | 0 | 0 | 0 | 1 | 1
User Story #12 Chat Panel | 1 |  |  | 6
Backend Development (Database & API) |  | Samishan | Done | 2.5 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1.5
Frontend Development |  | Manoram | Done | 2.5 | 0 | 0.5 | 0.5 | 0.5 | 1 | 2.5
Testing |  | Manoram | Done | 1 | 0 | 0 | 0 | 0 | 1 | 1
|  | Total |  | 15 | 0 | 1.5 | 3.75 | 4 | 4.5 | 12.75
|  | Ideal Time |  | 15 | -3 | -1.5 | 0.75 | 1 | 1.5 | 12.75

## Agile Sprint 5
Backlog Task & ID | Story | Assigned to | Status | Original | Day 1 | Day 2 | Day3 | Day 4 | Day 5 | Sprint
User Story #13 Book Property | 1 |  |  | 6
Backend Development (Database & API) |  | Samishan | Doing | 2 | 1 | 0 | 0.75 | 0 | 0.5 | 2.25
Frontend Development |  | Namrata | Doing | 3 | 1 | 0.5 | 0.75 | 0.75 | 0.5 | 3.5
Testing |  | Samishan | Doing | 1 | 0 | 0 | 0 | 0 | 0.5 | 0.5
User Story #14 Rent Property | 1 |  |  | 6
Backend Development (Database & API) |  | Manoram | Doing | 1.5 | 0 | 0 | 0 | 0 | 1 | 1
Frontend Development |  | Manoram | Doing | 3.5 | 0.5 | 0 | 0.5 | 0.5 | 2 | 3.5
Testing |  | Manoram | Doing | 1 | 0 | 0 | 0 | 0 | 0.5 | 0.5
User Story #15 Email Verification | 0.5 |  |  | 3
Backend Development (Database & API) |  | Gokarna | Doing | 1 | 1 | 0 | 0 | 0 | 0 | 1
Frontend Development |  | Gokarna | Doing | 1.5 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1.5
Testing |  | Gokarna | Doing | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5
User Story #16 Change Password | 0.5 |  |  | 3
Backend Development (Database & API) |  | Prathana | To Do | 1.5 | 0.5 | 0 | 0.5 | 1 | 0 | 2
Frontend Development |  | Prathana | To Do | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1
Testing |  | Prathana | To Do | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5
|  | Total |  | 18 | 3 | 0.5 | 3 | 3.25 | 7 | 17.75
|  | Ideal Time |  | 18 | -0.6 | -3.1 | -0.6 | -0.35 | 3.4 | 17.75

## Agile Sprint 6
Backlog Task & ID | Story | Assigned to | Status | Original | Day 1 | Day 2 | Day3 | Day 4 | Day 5 | Sprint
User Story #17 Recommend Properties Near Me | 1 |  |  | 6
Backend Development (Database & API) |  | Gokarna | Done | 2 | 0 | 0 | 1 | 0.5 | 0.5 | 2
Frontend Development |  | Gokarna | Done | 3 | 0 | 0 | 1.5 | 0.75 | 1 | 3.25
Testing |  | Gokarna | Done | 1 | 0 | 0 | 0.5 | 0 | 0.5 | 1
User Story #18 Rate Property | 0.5 |  |  | 3
Backend Development (Database & API) |  | Prathana | Done | 2 | 0 | 0.5 | 0 | 1.5 | 0 | 2
Frontend Development |  | Prathana | Done | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0.5
Testing |  | Prathana | Done | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0.5
User Story #19 Post Comment | 0.5 |  |  | 3
Backend Development (Database & API) |  | Samishan | Done | 1 | 0 | 0.5 | 0 | 0 | 0 | 0.5
Frontend Development |  | Samishan | Done | 1 | 0 | 0 | 1 | 0 | 0 | 1
Testing |  | Samishan | Done | 1 | 0 | 0 | 0 | 0 | 0.5 | 0.5
User Story #20 Like Comment | 0.5 |  |  | 3
Backend Development (Database & API) |  | Samishan | Done | 1 | 0 | 0.5 | 0 | 0 | 0 | 0.5
Frontend Development |  | Samishan | Done | 1 | 0 | 0 | 1 | 0 | 0 | 1
Testing |  | Samishan | Done | 1 | 0 | 0 | 0 | 0 | 0.5 | 0.5
User Story #21 Watch My Reviews | 0.5 |  |  | 3
Backend Development (Database & API) |  | Manoram | Done | 1 | 0 | 0 | 0 | 0 | 1 | 1
Frontend Development |  | Manoram | Done | 1.5 | 0 | 0.5 | 0.5 | 0 | 0.5 | 1.5
Testing |  | Manoram | Done | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5
User Story #22 Report Property | 1 |  |  | 6
Backend Development (Database & API) |  | Namrata | Done | 3 | 0 | 0.5 | 1 | 0 | 1.5 | 3
Frontend Development |  | Namrata | Done | 2 | 0 | 0 | 0 | 0.5 | 1.5 | 2
Testing |  | Namrata | Done | 1 | 0 | 0 | 0 | 0 | 1 | 1
User Story #23 Report Comment | 1 |  |  | 6
Backend Development (Database & API) |  | Namrata | Done | 3 | 0 | 0.5 | 1 | 0 | 1.5 | 3
Frontend Development |  | Namrata | Done | 2 | 0 | 0 | 0 | 0.5 | 1.5 | 2
Testing |  | Namrata | Done | 1 | 0 | 0 | 0 | 0 | 1 | 1
|  | Total |  | 30 | 0 | 3 | 7.5 | 4.75 | 13 | 28.25
|  | Ideal Time |  | 30 | -6 | -3 | 1.5 | -1.25 | 7 | 28.25

## Agile Sprint 7
Backlog Task & ID | Story | Assigned to | Status | Original | Day 1 | Day 2 | Day3 | Day 4 | Day 5 | Sprint
User Story #24 Forgot Password | 1 |  |  | 6
Backend Development (Database & API) |  | Prathana | Done | 4 | 0 | 0.5 | 0.5 | 0 | 3 | 4
Frontend Development |  | Prathana | Done | 1.5 | 0 | 0 | 0 | 0 | 1.5 | 1.5
Testing |  | Prathana | Done | 0.5 | 0 | 0 | 0 | 0 | 0.25 | 0.25
User Story #25 Login With Google | 1 |  |  | 6
Backend Development (Database & API) |  | Gokarna | Done | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1
Frontend Development |  | Gokarna | Done | 4.5 | 0 | 0 | 0 | 2 | 2 | 4
Testing |  | Gokarna | Done | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5
User Story #26 Login With Facebook | 1 |  |  | 6
Backend Development (Database & API) |  | Samishan | Done | 1 | 0 | 0 | 0 | 0 | 0.75 | 0.75
Frontend Development |  | Samishan | Done | 4 | 0 | 0 | 0 | 0 | 3 | 3
Testing |  | Samishan | Done | 1 | 0 | 0 | 0 | 0 | 0.5 | 0.5
User Story #27 Rate Owner | 1 |  |  | 6
Backend Development (Database & API) |  | Namrata | Done | 1.5 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1.5
Frontend Development |  | Namrata | Done | 3.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 3.5
Testing |  | Namrata | Done | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total |  | 24 | 0.5 | 1 | 1.5 | 4 | 13.5 | 20.5
|  | Ideal Time |  | 24 | -4.3 | -3.8 | -3.3 | -0.8 | 8.7 | 20.5

## Agile Sprint 8
Backlog Task & ID | Story | Assigned to | Status | Original | Day 1 | Day 2 | Day3 | Day 4 | Day 5 | Sprint
User Story #27 Report User | 0.5 |  |  | 3
Backend Development (Database & API) |  | Namrata | Done | 1.5 | 0 | 0.5 | 1 | 0 | 0 | 1.5
Frontend Development |  | Namrata | Done | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 1
Testing |  | Namrata | Done | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0.5
User Story #28 Logout | 0.5 |  |  | 3
Backend Development (Database & API) |  | Prathana | Done | 2 | 0 | 2 | 0 | 0 | 0 | 2
Frontend Development |  | Prathana | Done | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0.5
Testing |  | Prathana | Done | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0.5
User Story #29 Delete Account | 0.5 |  |  | 3
Backend Development (Database & API) |  | Gokarna | Done | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0.5
Frontend Development |  | Gokarna | Done | 2 | 0 | 1.5 | 0 | 0.5 | 0 | 2
Testing |  | Gokarna | Done | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0.5
|  | Total |  | 9 | 0.5 | 5.5 | 1 | 2 | 0 | 9
|  | Ideal Time |  | 9 | -1.3 | 3.7 | -0.8 | 0.2 | -1.8 | 9

## User Story
User Story | Acceptance Criteria
As a user, I want, to register an account so that I can login in Homepoint. | Users must enter valid information in required fields.
As a user, I want, to login so that I can get authentecated in Homepoint. | I can enter credentials from registered information.
As a user, I want to create an account through google auth so that I can login with google in Homepoint. | I can create account via google
As a user, I want to create an account through facebook auth so that I can login with facebook in Homepoint. | I can create account via facebook
As a user, I want to choose and select an image in profile page so that I can change my profile picture. | I can see my profile image
As a user, I want to enter new details for my profile so that I can change my profile information. | I can see my profile details
As a user, I want to choose "forgot password" option from login page so that I can recover my account. | I can receive email to reset my password
As a user, I want to create new password so that I can change my account password. | Users must enter valid and strong password
As a user, I want to delete my account so that I can remove my information from Homepoint. | I will become annonymous user in the system.
As a user, I want to have a logout button so that I can log out from the browser. | User must have logged in to the system.
As a userr, I want to receive an email so that I can verify my activities. | User must have provided a valid email.
As a user, I want to add a property details so that I can list my property in the website. | User must select a property type and fill all the required fields.
As a user, I want to upload images so that my property listings in more informative. | User must upload at least one image.
As a user, I want to change details of my listing so that I can update my listing. | I can see my listing details
As a user, I want to create rooms and its features in property listings so that I can add rooms in hotels listing. | User must enter valid information in required fields
As a user, I want to change details of rooms added in a property so that I can update rooms information. | User can see added rooms of the property
As a user, I want to go to owner chat panel so that I can conversate as a owner of the property listing. | I can see owner chat panel
As a user, I want to go to customer chat panel so that I can conversate as a customer of the property listing. | I can see customer chat panel
As a user, I want to send messages to other users so that I can send replies to my customers. | I can see chat panel
As a user, I want to send images to other users in chat so that I can send replies to my customers. | I can see chat panel
As a user, I want to have a rate button so that I can give rating to the owner of the property listing. | I can see chat panel
As a user, I want to have a report button for user so that I can report the user. | User must provide valid reason for reporting.
As a user, I want to go to my dashboard page so that I can see my account status. | I can see dashboard page
As a user, I want to go to my dashboard page so that I can go to my property listing page. | I can see dashboard page
As a user, I want to go to my dashboard page so that I can go to my booking history page. | I can see dashboard page
As a user, I want to go to my dashboard page so that I can go to my renting history page. | I can see dashboard page
As a user, I want to browse property listings so that I can find hostels | I can view hostels information.
As a user, I want to browse property listings so that I can find rooms | I can view rooms information.
As a user, I want to browse property listings so that I can find apartments | I can view apartments information.
As a user, I want to browse property listings so that I can find hotels | I can view hotels information.
As a user, I want to browse property listings so that I can find other properties | I can view other properties information.
As a user, I want to enter a location so that I can find properties around that location. | User can fill search bar.
As a user, I want to allow the system to have my location so that I can find properties listings around my place. | User must share location access to the system.
As a user, I want to filter the property listing ordered by rating so that I can filter top to least rated properties. | User can browse best reviewed properties.
As a user, I want to filter the property listing ordered by price so that I can filter afoordable properties. | User can browse affordable properties.
As a user, I want to filter the property listing ordered by latest date so that I can find latest properties. | User can see latest listed properties.
As a user, I want to enter a keyword so that I can find properties with that keyword. | I can view search result page
As a user, I want to select a property so that I can view details of that property | I can see details page
As a user, I want to make payment so that I can book a property. | User must enter valid payment details.
As a user, I want to rent a property so that I can move that property to rented list. | User can view property edtails.
As a user, I want to have a history page so that I can see renting history. | User must have rented the property.
As a user, I want to give rating to the property so that I can post a review on the property. | User must write a short review.
As a user, I want to write a comment so that I can reply on other comment. | User must write a short comment.
As a user, I want to like comments so that I can add likes to that comment. | User can view reviews.
As a user, I want to go to dashboard page so that I can see my reviews on properties. | User can see dashboard page.
As a user, I want to have an edit option on my reviews so that I can update my reviews. | User can see reviews page.
As a user, I want to have report button for properties so that I can report properties. | User must provide valid reason for reporting.
As a user, I want to have report button for properties so that I can report properties. | User must provide valid reason for reporting.
As a user, I want to have report button for comments so that I can report comments. | User must provide valid reason for reporting.

## User Story with priority
Feature ID | Featrue Name | User | As a | Priority | I want to | so that | Acceptance Crieteria
F1 | Register | 1 | User | High | register an account | I can login in Homepoint | Users must enter valid information in required fields.
F2 | Login | 2 | User | High | login | I can get authentecated in Homepoint | I can enter credentials from registered information.
F3 | Update Profile | 3.1 | User | High | choose and select an image | I can change my profile picture | I can see my profile image
|  | 3.2 |  |  | enter new details for my profile | I can change my profile information | I can see my profile details
|  | 3.3 |  |  | delete my account | I can remove my information from Homepoint | I will become annonymous user in the system.
F4 | User Dashboard | 4.1 | User | High | go to my dashboard page | I can see my account status | I can see dashboard page
|  | 4.2 |  |  | go to my dashboard page | I can go to my property listing page | I can see dashboard page
|  | 4.3 |  |  | go to my dashboard page | I can go to my booking history page | I can see dashboard page
|  | 4.4 |  |  | go to my dashboard page | go to my renting history page | I can see dashboard page
F5 | Create product list | 5.1 | User | High | add a property details | I can list my property in the website | User must select a property type and fill all the required fields.
|  | 5.2 |  |  | upload images | my property listings in more informative | User must upload at least one image.
F6 | Update property listing | 6 | User | High | change details of my listing | I can update my listing | I can see my listing details
F7 | Add rooms and features to property listing | 7.1 | User | High | create rooms and its features in property listings | I can add rooms in hotels listing | User must enter valid information in required fields
|  | 7.2 |  |  | change details of rooms added in a property | I can update rooms information | User can see added rooms of the property
F8 | Browse Properties | 8.1 | User | High | browse property listings | I can find hostels | I can view hostels information.
|  | 8.2 |  |  | browse property listings | I can find rooms | I can view rooms information.
|  | 8.3 |  |  | browse property listings | I can find apartments | I can view apartments information.
|  | 8.4 |  |  | browse property listings | I can find hotels | I can view hotels information.
|  | 8.5 |  |  | browse property listings | I can find other properties | I can view other properties information.
F9 | View Property Details | 9 | User | High | select a property | I can view details of that property | I can see details page
F10 | Search Properties | 10.1 | User | High | enter a location | I can find properties around that location | User can fill search bar
|  | 10.2 |  |  | enter a keyword | I can find properties with that keyword | I can view search result page
F11 | Filter Our Properties | 11.1 | User | High | filter the property listing ordered by rating | I can filter top to least rated properties | User can browse best reviewed properties.
|  | 11.2 |  |  | filter the property listing ordered by price | I can filter afoordable properties | User can browse affordable properties.
|  | 11.3 |  |  | filter the property listing ordered by latest date | I can find latest properties | User can see latest listed properties.
F12 | Chat Panel | 12.1 | User | High | go to owner chat panel | I can conversate as a owner of the property listing | I can see owner chat panel
|  | 12.2 |  |  | go to customer chat panel | I can conversate as a customer of the property listing | I can see customer chat panel
|  | 12.3 |  |  | send messages to other users | I can send replies to my customers | I can see chat panel
|  | 12.4 |  |  | send images to other users in chat | I can send replies to my customers | I can see chat panel
F13 | Book Property | 13 | User | High | make payment | I can book a property | User must enter valid payment details.
F14 | Rent Property | 14.1 | User | High | rent a property | I can move that property to rented list | User can view property edtails.
|  | 14.2 |  |  | have a history page | I can see renting history | User must have rented the property.
F15 | Email Verification | 15 | User | Medium | receive an email | I can verify my activities | User must have provided a valid email.
F16 | Change Password | 16 | User | Medium | create new password | I can change my account password | Users must enter valid and strong password
F17 | Recommend Properties Near Me | 17 | User | Medium | allow the system to have my location | I can find properties listings around my place | User must share location access to the system
F18 | Rate Property | 18 | User | Medium | give rating to the property | I can post a review on the property | User must write a short review.
F19 | Post Comment | 19 | User | Medium | write a comment | I can reply on other comment | User must write a short comment.
F20 | Like Comment | 20 | User | Medium | like comments | I can add likes to that comment | User can view reviews.
F21 | Watch My Reviews | 21.1 | User | Medium | go to dashboard page | I can see my reviews on properties | User can see dashboard page.
|  | 21.2 |  |  | have an edit option on my reviews | I can update my reviews | User can see reviews page.
F22 | Report Property | 22 | User | Medium | have report button for properties | I can report properties | User must provide valid reason for reporting.
F23 | Report Comment | 23 | User | Medium | have report button for properties | I can report properties | User must provide valid reason for reporting.
F24 | Forgot Password | 24 | User | Medium | choose "forgot password" option from login page | I can recover my account. | I can receive email to reset my password
F25 | Login With Google | 25 | User | Medium | create an account through google auth | login with google in Homepoint | I can create account via google
F26 | Login With Facebook | 26 | User | Medium | create an account through facebook auth | I can login with facebook in Homepoint. | I can create account via facebook
F27 | Rate Owner | 27 | User | Medium | have a rate button s | I can give rating to the owner of the property listing. | I can see chat panel
F28 | Report User | 28 | User | Medium | have a report button for user | I can report the user. | User must provide valid reason for reporting.
F29 | Logout | 29 | User | Low | have a logout button | I can log out from the browser. | User must have logged in to the system.
F30 | Delete Account | 30 | User | Low | delete my account | I can remove my information from Homepoint. | I will become annonymous user in the system.

## Release Plan
At Risk | Sprint | User Story Name | Feature Type | Start | Finish | Story Points | (In Hours) | Status | Release Date | Goal
FALSE | 1 | Login | Functionality | 2022-05-10 | 2022-05-13 | 1 | 5.75 | Done | 2022-05-15 | TRUE
FALSE | 1 | Register | Functionality | 2022-05-11 | 2022-05-13 | 1 | 5.75 | Done | 2022-05-15 | TRUE
FALSE | 1 | Update Profile | Functionality | 2022-05-10 | 2022-05-14 | 1 | 6 | Done | 2022-05-15 | TRUE
FALSE | 1 | User Dashboard | Functionality | 2022-05-10 | 2022-05-14 | 1 | 2.25 | Done | 2022-05-15 | TRUE
At Risk | Sprint | User Story Name | Feature Type | Start | Finish | Story Points | (In Hours) | Status | Release Date | Goal
FALSE | 2 | Create property listing | Functionality | 2022-05-17 | 2022-05-20 | 2 | 11.5 | Done | 2022-05-22 | TRUE
FALSE | 2 | Update property listing | Functionality | 2022-05-17 | 2022-05-20 | 1 | 4.75 | Done | 2022-05-22 | TRUE
FALSE | 2 | Add rooms and features to property listing | Functionality | 2022-05-17 | 2022-05-20 | 1 | 1.5 | Done | 2022-05-22 | TRUE
FALSE | 2 | Browse properties | Functionality | 2022-05-17 | 2022-05-20 | 1 | 1 | Done | 2022-05-22 | TRUE
FALSE | 2 | View property details | Functionality | 2022-05-17 | 2022-05-20 | 1 | 4.25 | Done | 2022-05-22 | TRUE
At Risk | Sprint | User Story Name | Feature Type | Start | Finish | Story Points | (In Hours) | Status | Release Date | Goal
TRUE | 3 | Search Properties | Functionality | 2022-05-23 | -- | 1 | 1.5 | Done | -- | FALSE
TRUE | 3 | Filter Out Properties | Functionality | 2022-05-23 | -- | 1 | 4.25 | Done | -- | FALSE
TRUE | 3 | Chat Panel | Functionality | 2022-05-24 | -- | 2 | 3 | Done | -- | FALSE
At Risk | Sprint | User Story Name | Feature Type | Start | Finish | Story Points | (In Hours) | Status | Release Date | Goal
FALSE | 4 | Search Properties | Functionality | 2022-06-01 | 2022-06-02 | 0.5 | 2.75 | Done | 2022-06-05 | TRUE
FALSE | 4 | Filter Out Properties | Functionality | 2022-05-31 | 2022-06-03 | 1 | 6 | Done | 2022-06-05 | TRUE
FALSE | 4 | Chat Panel | Functionality | 2022-05-31 | 2022-06-03 | 1 | 5 | Done | 2022-06-05 | TRUE
At Risk | Sprint | User Story Name | Feature Type | Start | Finish | Story Points | (In Hours) | Status | Release Date | Goal
FALSE | 5 | Book Property | Functionality | 2022-06-06 | 2022-06-10 | 1 | 6.25 | Done | 2022-06-12 | TRUE
FALSE | 5 | Rent Property | Functionality | 2022-06-06 | 2022-06-10 | 1 | 5 | Done | 2022-06-12 | TRUE
FALSE | 5 | Email Verification | Functionality | 2022-06-06 | 2022-06-10 | 0.5 | 3 | Done | 2022-06-12 | TRUE
FALSE | 5 | Change Password | Functionality | 2022-06-06 | 2022-06-10 | 0.5 | 3.5 | Done | 2022-06-12 | TRUE
At Risk | Sprint | User Story Name | Feature Type | Start | Finish | Story Points | (In Hours) | Status | Release Date | Goal
FALSE | 6 | Recommend Properties Near Me | Functionality | 2022-06-15 | 2022-06-17 | 1 | 6.25 | Done | 2022-06-19 | TRUE
FALSE | 6 | Rate Property | Functionality | 2022-06-14 | 2022-06-16 | 0.5 | 3 | Done | 2022-06-19 | TRUE
FALSE | 6 | Watch My Reviews | Functionality | 2022-06-14 | 2022-06-17 | 0.5 | 3 | Done | 2022-06-19 | TRUE
FALSE | 6 | Post Comment | Functionality | 2022-06-14 | 2022-06-17 | 0.5 | 2 | Done | 2022-06-19 | TRUE
FALSE | 6 | Like Comment | Functionality | 2022-06-14 | 2022-06-17 | 0.5 | 2 | Done | 2022-06-19 | TRUE
FALSE | 6 | Report Comment | Functionality | 2022-06-14 | 2022-06-17 | 1 | 6 | Done | 2022-06-19 | TRUE
FALSE | 6 | Report Property | Functionality | 2022-06-14 | 2022-06-17 | 1 | 6 | Done | 2022-06-19 | TRUE
At Risk | Sprint | User Story Name | Feature Type | Start | Finish | Story Points | (In Hours) | Status | Release Date | Goal
FALSE | 7 | Login With Google | Functionality | 2022-06-20 | 2022-06-25 | 1 | 5.5 | Done | 2022-06-28 | TRUE
FALSE | 7 | Login With Facebook | Functionality | 2022-06-23 | 2022-06-25 | 1 | 4.25 | Done | 2022-06-28 | TRUE
FALSE | 7 | Forgot Password | Functionality | 2022-06-21 | 2022-06-25 | 1 | 5.75 | Done | 2022-06-28 | TRUE
FALSE | 7 | Rate User | Functionality | 2022-06-20 | 2022-06-25 | 1 | 5 | Done | 2022-06-28 | TRUE
At Risk | Sprint | User Story Name | Feature Type | Start | Finish | Story Points | (In Hours) | Status | Release Date | Goal
FALSE | 8 | Report User | Functionality | 2022-06-28 | 2022-07-01 | 0.5 | 3 | Done | 2022-07-03 | TRUE
FALSE | 8 | Delete Account | Functionality | 2022-06-29 | 2022-07-01 | 0.5 | 3 | Done | 2022-07-03 | TRUE
FALSE | 8 | Log out | Functionality | 2022-06-29 | 2022-07-01 | 0.5 | 3 | Done | 2022-07-03 | TRUE

## Map Board
Release Theme: Homepoint
The Backbone | Epic 1 | Epic 2 | Epic 3 | Epic 4 | Epic 5 | Epic 6 | Epic 7
Flesh on the backbone | User Creation | Profile | Property Listing | Browse Property | Chat Panel | Booking and Renting | Ratings and Reviews
Sprint/Iteration 1 | Register | Update Profile
(2022-05-10)-(2022-05-15) | Login | User Dashboard
Sprint/Iteration 2 |  |  | Create Property Listing
(2022-05-10)-(2022-05-15) |  |  | Update Property Listing
Add rooms and features
Sprint/Iteration 3 |  |  |  | View Property Details
(2022-05-10)-(2022-05-15) |  |  |  | Search Properties
Filter Properties
Sprint/Iteration 4 |  |  |  |  | Chat Panel
(2022-05-10)-(2022-05-15)
Sprint/Iteration 5 |  | Email Verification |  |  |  | Rent Property
(2022-05-10)-(2022-05-15) |  | Change Password |  |  |  | Book Property
Sprint/Iteration 6 | [6 empty] | Rate Property
(2022-05-10)-(2022-05-15) | [6 empty] | Like Comment
Watch Reviews
Sprint/Iteration 7
(2022-05-10)-(2022-05-15)
Sprint/Iteration 8 |  | Logout
(2022-05-10)-(2022-05-15) |  | Delete Account

## Agile Team
Homepoint
Name | Role
Manoram Baudel | Scrum Master/ Product Owner/ Developer
Namrata Bimali | Developer
Gokarna Adhikari | Developer
Samishan Thapa | Developer
Prathana Thapa Magar | Developer